## Fall
Project Description | Creating a tool for TAs to use in office hours to organize and prioritize student interaction. (webapp)
| Story Name | Description | Req | Effort | Priority | Dependency | Assignment | Sprint |  | Drop Deads
1 | TA Login | The TA should have a way to log into the web app. This should utilize OSU Central Auth to confirm they are part of OSU. | Product, software, Functional, qualitative, emergent | 2 | High | Related to 3 | Sam | 1 |  | Sprint 1 | 2017-10-20
43 | Refactor current code to work with PHPUnit | Refactor the code as the object-orientated style to make sure the PHPUnit test can be implemented in. | Product, software, nonFunctional, qualitative, emergent |  | High |  | All | 3
3 | Student Login | The student should have a way to log into the web app. This should utilize OSU Central Auth to confirm they are part of OSU. | Product, software, Functional, qualitative, emergent | 1 | High | Related to 1 | Sam | 1 |  | Sprint 3 | 2017-12-01
2 | Students need to add questions to the list | When a student is logged in, they should be able to fill out a form that will add a question to the list of questions. The form should include name of student, question text, when the student will be in office hours (either now or at a later time), and a list of related terms for the question. | Product, software, Functional, qualitative, emergent | 8 |  | Related to 4 | Bi |  |  | Sprint 2 | 2017-11-10
5 | Software needs to be able to host multiple classes | Need to be able to be a portal for multiple courses. Keep track of which TAs are in which course, which students are in which course. | Product, software, Functional, qualitative, emergent | 4 |  |  | Teng | 2
31 | Student can modify questions they own | If the student is the author of a question they should be able to edit the content of that question. | Product, software, Functional, qualitative, emergent | 2 | Medium |  | Chengxi | 3
11 | TA needs to change status of question/remove question (select all and delete) | TAs need to be able to clear, pending or assigned questions either one at a time or select multiple and delete when they have answered the question. | Product, software, Functional, qualitative, derived | 4 | High |  | Deqing | 3
8 | Student should be able to add themselves to an already written question | Questions should have a button when they are displayed to allow students to add themselves to the question. This button should add the name of the student to the list of interested students and increment the count of students wanting an answer to this question. | Product, software, Functional, qualitative, emergent | 2 |  |  | Bi | 2
9 | Student should be able to add themselves to the class | When a student logs in they should be able to select which class they are a part of. Once they have one class the system will default to taking them to that class. If they have more than one class they will be able to toggle between the courses via a dropdown menu. A button to add a course should always be available to the student with all the courses currently utilizing the webapp. | Product, software, Functional, qualitative, derived | 2 |  |  | Bi | 2
10 | Main entrance | There should be a front login page for students and TAs with a brief description of the product. | Product, software, nonFunctional, qualitative, | 2 |  |  | Chengxi | 2
39 | Fix unclickable buttons on question detail page | In TA question detail page, do not use button to show members' name. | Product, software, Functional, qualitative, emergent | 1 | High |  | Deqing | 3
12 | Software should be able to group students based on question and order priority based on number of students/time passed | Two stories: first sprint is the algorithm design, second is implementing and testing | Product, software, Functional, qualitative, emergent | 20 total (10 per sprint) | High |  | Chengxi | 1
13 | Students should be able to view other students question | Students should be able to see what questions are in the queue for office hours. | Product, software, Functional, qualitative, emergent | 2 |  |  |  | 2
40 | Icons need to update when adding yourself to a question | In TA question list page, the icon of assign button should be changed to prevent the misunderstanding by users. | Product, software, nonFunctional, qualitative, derived | 1 | High |  | Deqing | 3
15 | TA needs to pick which class they are working on | When a TA logs in, if they have multiple courses assigned to them, they need to be able to select which one they are currently working for. | Product, software, Functional, qualitative, emergent | 2 |  |  | Teng, Deqing | 2
16 | TA needs to assign themselves a question | TAs should be able to view the question queue and assign themselves questions to answer so that other TAs and students know someone will be answering the question. | Product, software, Functional, qualitative, emergent | 4 |  |  | Teng, Deqing | 2
17 | TA needs to be able to view the timestamp, contributors name, question text, number of students and their names, and if a TA has been assigned to it when viewing the question | Display of the question in the TA queue | Product, software, Functional, qualitative, emergent | 1 |  |  | Teng, Deqing | 2
18 | TA should view questions in a list format | Display of the question in the TA queue | Product, software, Functional, qualitative, emergent | 10 |  | Related to 17 | Teng, Deqing | 2
46 | Add interest description | When join in a question, students can add the description which why they interest in it. | Product, software, Functional, qualitative, emergent | 4 | Medium |  | Deqing | 3
35 | Limit error messages to toast | Reduce the error message shown to the users. | Product, software, nonFunctional, qualitative, derived | 2 | High |  | Kang | 3
21 | Admin should be able to add a course |  | Product, software, Functional, qualitative, emergent | 2 | High |  | Shannon | 2
22 | Admin should be able to add TAs to the course |  | Product, software, Functional, qualitative, emergent | 4 | High |  | Shannon | 2
23 | Set up (DB, webpages, etc.) | Need to set up all databases and skeleton webpages. Including a design documents (docs by mid week 2) | Product, system, Functional, qualitative, emergent | 20 | High |  | Teng, Kang | 1
24 | Tech review | Determine what frameworks will be used, if there are APIs currently available, etc. | Process, system, Functional, qualitative, emergent | 5 | High |  | Shannon | 1
25 | First time login | On first login the user decides if they are a TA or student. This is saved in a database for later use and determines which welcome screen they use. | Product, software, Functional, qualitative, emergent | 3 |  |  | Sam | 1
26 | TA can add a class/select class/registration |  | Product, software, Functional, qualitative, emergent | 4 |  |  | Bi | 1
27 | Logout | All users should be able to logout returned to the homepage | Product, software, Functional, qualitative, emergent |  |  |  | Shannon | 2
28 | Admin Login | need to have admin/instructor login | Product, software, Functional, qualitative, emergent | 2 |  |  | Shannon | 2
29 | List Animation Spike | Animating a re-ordering list on dummy data to figure out if and what libraries/frameworks to use | Product, software, nonFunctional, qualitative, emergent | 4 | High |  | Chengxi | 2
42 | Logout needs to logout ONID | The session_id which is generated by ONID login system should be deleted when logout to make sure the user can change the account after logout. | Product, software, Functional, qualitative, emergent | 1 | High |  | Kang | 3
44 | Error handler | When doing the actions, there should be a feedback that whether the operation is success or failed. | Product, software, Functional, qualitative, emergent | 6 | Medium |  | Kang | 3
32 | Security - limit access only to authorized users | Users should only be able to access the pages they are assigned to. For example, students should only be able to access the student dashboard, TAs can access TA view + student dashboard, Admins can see everything | Product, software, nonFunctional, qualitative, emergent | 4 | High |  | Sam | 3
33 | Click off modal dismisses | On all modals clicking outside of the modal should dismiss it | Product, software, Functional, qualitative, derived | 1 | High |  | Sam | 3
34 | Reword language throughout application | Go through system and reword labels to make clearer for users. Use language similar to Canvas | Product, software, nonFunctional, qualitative, derived | 1 | HIgh |  | Sam | 3
41 | Fix login experience between index versus welcome page | Make the welcome page to be the first page of the website. | Product, software, Functional, qualitative, emergent | 1 | High |  | Sam | 3
36 | Admin dashboard show course data | The admins can view all existed course data in the system. | Product, software, Functional, qualitative, emergent | 2 | High |  | Teng | 3
37 | Admin dashboard allow edit course info | The admins can edit the course information they created. | Product, software, Functional, qualitative, emergent | 2 | High |  | Teng | 3
38 | If function fails, don't lose data | When student adding classes, use database transaction to prevent data loss | Product, software, Functional, qualitative, emergent | 1 | High |  | Teng | 3
45 | Tagging the question | When posting a question, users can tag it with the keyword | Product, software, Functional, qualitative, emergent | 4 | Medium |  | Teng | 3
4 | Student can input question ahead of when they will be in office hours. | The student should be able to have access to the webapp before coming into office hours to see what questions are currently being asked, what questions are lined up to be asked, and to submit a question that they wish to ask when they come into office hours. | Product, software, Functional, qualitative, emergent | 1 |  | Related to 2
6 | View: student adds a question before office hours | Satisfied by 2: student will be logging in on own device. | Product, software, Functional, qualitative, emergent
7 | View: student adds a question during office hours | Satisfied by 2: student will be logging in on own device. | Product, software, Functional, qualitative, emergent
14 | If question has more than X number of people, notify the instructor via email (part of assign) | The system should email questions to the instructor if more than a certain threshhold of students have the same question in the same office hour block. This means that it is a question that most students have and office hour time shouldn't be used to answer it. | Product, software, Functional, qualitative, emergent | 5
19 | Students can delete their own questions if nobody interest in it | If the student is an author of a question they should be able to delete the question, unless there are other students on the question. | Product, software, Functional, qualitative, emergent | 1 |  |  |  |  | Scope: OSU, not going worry about course validation
20 | Student should be able to view a list of questions TA name if assigned | Display of the question in the student queue | Product, software, Functional, qualitative, emergent | 10 |  | Related to 17, 18
30 | Student class search | Student should be able to search through the list of all classes | Product, software, Functional, qualitative, derived | 3

## Winter
Number | User Story | Details | Prioirty
Search (classes, TAs, questions)
API (revamp) - Delete course
UI fixes
Pagenation of questions
Bug Fixes
First Encounter/First Experience
Testing Suite
Migrate onto same system/platform
Mobile
File upload
Saving/Generate reports of questions
Feeback system