## Sheet1
| Shannon | Sam | Deqing | Teng | Kang | Chengxi | Bi
2017-11-13 | Figured out how to put PHPUnit and Mocha on the server | Nothing, start work tomorrow | Fixed bugs in last sprint review | Started stories, read code, revised bugs | Solve logout problem, can't delete OSU service key | Started working on user stories, need to read Bi's code | Finished project schedule, updated phpunit document, set up free account on AWS, implement autotest
2017-11-14 | Still need to write readme, documenting scrums | Started looking at login and welcome and designing the new experience looking to get done by tomorrow | Working on parameter validation, want js functions more robost, want to write more tests | Want to clarify a user story | Looked at source code currently have, tried to deploy server to his server, trying to figure out how to solve it | Set up dev environment and working on user story and reading source code related to user story think he can get it done before next Monday, set up new branch | Working on AWS
2017-11-15 | Working on readme | Graded | Worked on refactoring of sprint 2 code, fixed previous bugs, working on stories for delete | Finished the story about students selecting class and refactoring code almost done with admin dashboard | Added tests for student dashboard, refactored php file for that page | Working on user story for question they posted | Working on code from previous sprint, trying to test
2017-11-16 | Working on the readme | Did log in redirect, if there is an error it will redirect to welcome, logout takes to welcome | Still working on delete questions and set up framework for restful api | Finished the admin dashboard to show the course and added the course and fixed the bug when student select to delete, if something fails it will roll back. | Added toast and question list page, some bugs in the page, will focus on fixing bugs tomorrow | Working on editing question they posted, shows description, need to rewrite database | Refactor get question list file and make some public function and checks permissions
2017-11-17 | None, demoed phpunit yesterday, will continue maintaining scrum | Integrated with slack github notifications for pull requests and comments | Still working on delete questions and something is wrong, will fix bugs over weekend | Started working on tagging | Fixing bug on student question, just read the source code, can fix by weekend | Working on user story, can receive the question description and title and make them appear, rewrite the database, can finish by Monday | Finished refactoring and pull request
2017-11-20 | Monitoring scrum | Started looking at security, will finish soon | Haven't finished part, plan to finish, back end done of delete question | Still working on stories | Finished student question list bug | Almost finished user story, need help on database | Writing tests
2017-11-21 | Monitoring scrum | Continue working on security | Delete question is almost done, unit testing | Almost done in user story, want to improve sprint | Added toast to the TA question list page, another bug in class list | Almost finished user story need help on SQL | Reviewed schedule and details to talk about function and talk about user tests
2017-11-22 | Monitoring scrum | Still working on security | Finished delete question, interest is difficult | Still working on tagging will finish this weekend | Working student question list page and still fixing bugs | Finished user story with help of Bi, will do tests | Reviewed website and checked everything works, found some bugs
2017-11-27 | Monitoring Scrum | Finished all user stories, rewording, security, modal dismiss, etc. Reworked log in experience. Should redirect to homepage. Unit tests to come | Started to test all APIs, finish tomorrow | Finished all the user stories and all unit tests, branch can be merged | Added toast on admin page, fixed bugs | Doing tests | Organize the unit tests
2017-11-28 | Monitoring Scrum | Merged everything, two conflicts, doing unit tests | Finished the api test on the questions and is fine but need courses to be done because don't have permission, all of the API tests can't go through at once because the accounts need to be done. | Submitted everything free to help. | Preparing to unit test | Getting ready of for user tests | Did user studies
2017-11-29 | Set up user reviews | Still working on unit tests | Modified api tests because some updated yesterday | Purged database and fixed bug | Still working on unit tests | Continue working on tests because of db change | Did user test and will do more user tests tomorrow
2017-11-30 | Uploaded scrum photos, monitoring scrum, conduct sprint retro | Did unit tests | Did API test and wrote test cases, most of the api has been tested some parameters are tricky, uploaded the results | Done, check database everything is fine, posted test results | Had issues with unit testing the UI and using framework, got the logout working | Doing unit tests and had some issues, the test couldn't get the correct info | Did the user tests and need one more person
2017-12-01 | Monitoring Scrum | Wasn't able to add unit tests, will do later today | Helped Chengxi to do API test | Done | Didn't find difference | Uploaded tests for API | Finished the sprint report

## Sheet3
user story | learnability | memorability | efficiency | error rate
security |  |  |  | x | Only those who should have access to those pages have access. | User study in the lab
rewording | x |  |  |  | By rewording the pages, the language is more consistent with preexisting systems which the students will use in conjuction with our system. | User study in the field
rework index page |  | x | x
students modify question | x | x | x |  | Students can update the question rather than deleting and recreating reducing the number of steps. | User study in the field

## Sheet2
Refactor
addNewQuestion.php
assign_question.php | create a check user function to use in multiple locations
checkUserType.php
check_user.php
get_question_detail
joininquestion
query_class
question_list
quitQuestion