## Sheet1
Name | Sam (Product Owner) | Kang (Scrum Master) | Deqing (Developer) | Bi (Developer) | Chengxi (Developer) | Teng (Developer) | Shannon (Developer)
Oct. 23 | Discuss what need to do in sprint 2 | Read related document to figure out what need to record in sprint 2 | Discuss with other team members about the whole system | Work on student part | Work on algorithm | Read existing code | Read existing code
Oct. 24 | Distribute sprint 2 work | Record discussion and discuss with others about the modification of requirement | Draw paper prototype and discuss with others | Decide which components in student part should be modified in the sprint 2 | Work on algorithm | Draw paper prototype and discuss with others | Discuss with others about the details of the system
Oct. 25 | Give suggestions about implementation | Modify database schema to meet new requiement and record the daily meeting | Discuss with Teng about the TA part | Work on student part | Work on algorithm | Discuss with Deqing about the TA part | Read existing code and do research about login part
Oct. 26 | Give suggestions and feedbacks | Make progress doc and record daily meeting | Discuss about whether need to modify the existing API | Discuss with Chengxi about integrating their components | Discuss with Bi about integrating their components | Discuss with Deqing about the implementation of TA part | Start to implement the Logout part
Oct. 27 | Read user stories to ensure everything goes well | Get progress doc done and record daily meeting | Start Implement the front end of TA dashboard | Work on student question List and discuss with Chengxi about integration | Discuss with Bi about integrating their components | Start Implement the back end of TA dashboard | Work on Admin login part and logout part
Oct. 30 | Read documents | Record daily meeting | Work on the front end of TA dashboard | Implement student list enable student add themselves to a particular question | Get integration done | Work on the backend of TA dashboard and question list | Work on Admin login part and logout part
Oct. 31 | Read code pushed so far | Record daily meeting | Work on the front end of question list | Get student question list done | Test algorithm | Work on the backend of question list | Work on Admin login part and logout part