## Sheet1
| Task | Progress(percentage) | Status | Problem or Troubles
Shannon:
| Admin Login | 0% | working on
| Logout | 0% | working on
| Admin Dashboard(add course and assign TA) | 0% | not start
Teng, Deqing | TA Dashboard(pick class) | 0% | not start
| TA Question List Page(assign) | 0% | not start
| Question Detail Page | 0% | not start
Chenxi
| Home Page | 0% | not start
| Sorting Algorithm | 0% | not start | Need to communicate with Bi
Bi
| Student Class List Page(join class) | 0% | not start
| Student Question List Page(add to question) | 0% | not start | Need to communicate with Chenxi
| Create Question Page | 0% | not start