## Sheet1
| Task | Progress(percentage) | Status | Problem or Troubles
Shannon:
| Admin Login | 90% | working on
| Logout | 90% | working on
| Admin Dashboard(add course and assign TA) | 60% | working on
Teng, Deqing | TA Dashboard(pick class) | 100% | done
| TA Question List Page(assign) | 100% | done
| Question Detail Page | 10% | working on
Chengxi
| Home Page | 95% | working on
| Sorting Algorithm | 100% | done | Need to communicate with Bi
Bi
| Student Class List Page(join class) | 50% | working on
| Student Question List Page(add to question) | 100% | done | Need to communicate with Chengxi
| TA Question List Page(delete question) | 0% | not start | Depend on TA Question List(Teng, Deqing)
Photo! Photo!! Photo!!!